## 📊 Overview
APAC Relocation — 90-Day Growth Scheduler
AEO · SEO · Social Media ¦ June–September 2026 ¦ Target: Singapore ¦ Prepared by AEO-APP
Phase | Weeks | Total Tasks | Fully Auto | Partial | AI-Assisted | Est. Hours Saved
Month 1 — Foundation | Wks 1–4 | 31 | 13 | 12 | 6 | ~14 hrs
Month 2 — Growth | Wks 5–8 | 30 | 9 | 16 | 5 | ~15 hrs
Month 3 — Acceleration | Wks 9–12 | 36 | 12 | 14 | 10 | ~20 hrs
TOTAL | Weeks 1–12 | 97 | 34 | 42 | 21 | ~48 hrs
AUTOMATION LEGEND
✅ Full automation | Runs without human input once set up. Saves 75–100% of task time.
⚡ Partial automation | AI drafts the output. Human reviews and approves before it goes live. Saves 50–70% of task time.
★ AI-assisted | Human leads the work. AI accelerates research, writing, or analysis. Saves 25–40% of task time.
Auto (team) | Task runs automatically with no human time required at all.
90-DAY KPI TARGETS
KPI | Baseline |  | 30-Day Target |  | 90-Day Target
AEO score | 28/100 |  | 45/100 |  | 65/100
AI engines citing APAC | 0 of 5 |  | 2 of 5 |  | 4 of 5
Organic traffic (est.) | ~20K/mo |  | 22K/mo |  | 28K+/mo
Blog posts published | Stale (2022) |  | 4 new posts |  | 12 new posts
LinkedIn followers | 1,648 |  | 1,900 |  | 2,500+
Instagram followers | ~600 |  | 900 |  | 1,500
YouTube subscribers | <200 |  | 300 |  | 600
TikTok account | Not present |  | Account live |  | 500+ followers
Google reviews | Unknown |  | +15 reviews |  | 40+ new reviews
Inbound leads | Baseline |  | +15% |  | +35%
AI TOOL STACK & MONTHLY BUDGET
Tool |  |  | Purpose |  |  | Cost/month
Claude (Anthropic) |  |  | Content drafts, schema, captions, emails, analysis |  |  | S$25–50
Buffer / Later |  |  | Social scheduling — all 5 platforms |  |  | S$30–50
HubSpot Starter |  |  | Review automation, lead response, CRM triggers |  |  | S$80
Canva Pro + AI |  |  | Social graphics, carousels, infographics |  |  | S$20
CapCut (free) / Descript |  |  | Auto-captions on TikToks + Reels / YouTube editing |  |  | S$0–20
Looker Studio |  |  | Automated reporting dashboard (GA4 + GSC + social) |  |  | Free
Surfer SEO / Clearscope |  |  | Content optimisation vs top-ranking pages |  |  | S$100–120
Ahrefs Lite |  |  | Backlink tracking, competitor monitoring, keywords |  |  | S$120
Google Alerts |  |  | Competitor monitoring — brand names + keywords |  |  | Free
Make (Integromat) |  |  | Connects all tools — triggers indexing, review requests |  |  | S$20–50
Birdeye / NiceJob |  |  | Automated Google Review collection post-move |  |  | S$100–150
TOTAL ESTIMATE | [5 empty] | S$495–710/mo

## M1 — Foundation
APAC Relocation ¦ Month 1 — Foundation
Make APAC technically eligible to be cited by AI engines. Fix SEO issues. Launch content infrastructure.
✅ Full automation |  | ⚡ Partial (AI drafts, you approve) |  |  | ★ AI-assisted
TASK AREA / DELIVERABLE |  | Automation | AI Tool | Team | Est. Hrs | Week | Status | Notes
CONTENT
Content | Write + publish SG to UK guide (2,500 words) | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 2 | Not started
Content | Set up 12-week editorial calendar | ★ AI-assisted | Claude + Notion | Marketing | 0.5 hrs | Week 2 | Not started
Content | Write + publish SG to Australia guide (2,500 words) | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 3 | Not started
Content | Expand 30+ thin destination pages (600 words each) | ⚡ Partial | Claude + Surfer SEO | Marketing | 3.0 hrs | Week 3 | Not started
Content | Write + publish Moving Cost guide (2,000 words) | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 4 | Not started
Content | Monthly email newsletter draft | ⚡ Partial | Claude + Mailchimp AI | Marketing | 0.5 hrs | Week 4 | Not started
SEO / AEO
SEO / AEO | Fix all spelling errors site-wide ('employess' etc.) | ✅ Full automation | Claude / Grammarly | Marketing | 0.5 hrs | Week 1 | Not started
SEO / AEO | Rewrite all 20+ meta titles + descriptions | ✅ Full automation | Claude + CSV export | Marketing | 0.5 hrs | Week 1 | Not started
SEO / AEO | Add FAQ schema — top 5 service pages | ✅ Full automation | Claude → Developer | Developer | 1.0 hrs | Week 1 | Not started
SEO / AEO | LocalBusiness + Review schema on homepage | ⚡ Partial | Claude → Developer | Developer | 1.0 hrs | Week 1 | Not started
SEO / AEO | Create + publish /llms.txt file | ✅ Full automation | Claude → Developer | Developer | 0.5 hrs | Week 1 | Not started
SEO / AEO | Submit updated sitemap to GSC + Bing | ✅ Full automation | GSC + Bing API | Developer | 0.2 hrs | Week 1 | Not started
SEO / AEO | Submit all new content for indexing | ✅ Full automation | Make + GSC + Bing API | Developer | 0.2 hrs | Week 2 | Not started
SEO / AEO | Backlink outreach — 5 expat/property blogs | ⚡ Partial | Claude + Hunter.io | Marketing | 1.0 hrs | Week 3 | Not started
SEO / AEO | Set up Google Alerts for brand + competitors | ✅ Full automation | Google Alerts | Marketing | 0.2 hrs | Week 3 | Not started
SEO / AEO | Full technical crawl + schema validation | ★ AI-assisted | Screaming Frog + Claude | Developer | 1.5 hrs | Week 4 | Not started
SEO / AEO | AEO baseline test: 10 prompts × 5 engines | ★ AI-assisted | Claude + Notion | Marketing | 1.0 hrs | Week 4 | Not started
SEO / AEO | Google Review follow-up sequence | ✅ Full automation | HubSpot automation | Auto | Auto | Week 4 | Not started
SOCIAL
Social | Set up TikTok business account + bio | ★ AI-assisted | Claude → Social Media | Social Media | 0.5 hrs | Week 1 | Not started
Social | LinkedIn content calendar Weeks 2–4 (auto-schedule) | ✅ Full automation | Claude + Buffer | Social Media | 0.5 hrs | Week 2 | Not started
Social | LinkedIn: 3 posts live (auto-published) | ✅ Full automation | Buffer | Auto | Auto | Week 2 | Not started
Social | LinkedIn: 3 posts (company story, IAM, expat tips) | ✅ Full automation | Claude + Buffer | Auto | Auto | Week 3 | Not started
Social | Instagram: 3 posts + Reel (piano packing) | ⚡ Partial | Claude + Canva AI | Social Media | 1.5 hrs | Week 3 | Not started
Social | TikTok Video 1: Packing day walkthrough | ⚡ Partial | Claude + CapCut AI | Social Media | 1.0 hrs | Week 3 | Not started
Social | Facebook launch: 3 posts | ⚡ Partial | Claude + Canva AI | Social Media | 1.0 hrs | Week 4 | Not started
Social | YouTube: channel setup + brand video (60s) | ★ AI-assisted | Claude → Video | Video | 3.0 hrs | Week 4 | Not started
Social | TikTok: 2 videos (AU customs, SG→London) | ✅ Full automation | Claude + CapCut AI | Social Media | 1.0 hrs | Week 4 | Not started
REPORTING
Reporting | Week 4 performance review report | ⚡ Partial | Claude + GA4 + GSC | Marketing | 0.5 hrs | Week 4 | Not started
OUTREACH
Outreach | Email 20 recent clients requesting Google Reviews | ✅ Full automation | Claude + HubSpot | Auto | Auto | Week 1 | Not started
Outreach | Create profiles: Expat.com, InterNations, Reddit | ★ AI-assisted | Claude → Marketing | Marketing | 0.5 hrs | Week 2 | Not started
Outreach | Reddit + Expat.com forum answers (8 posts) | ⚡ Partial | Claude → Marketing | Marketing | 0.5 hrs | Week 3 | Not started
MONTH SUMMARY
Total tasks | 31
Fully automated | 13
Partial automation | 12
AI-assisted | 6
Est. total hours | 26 hrs
Est. hours saved by AI | ~14 hrs

## M2 — Growth
APAC Relocation ¦ Month 2 — Growth
Scale content, activate all social channels, build AEO citations. Target: appearing in 2+ AI engines.
✅ Full automation |  | ⚡ Partial (AI drafts, you approve) |  |  | ★ AI-assisted
TASK AREA / DELIVERABLE |  | Automation | AI Tool | Team | Est. Hrs | Week | Status | Notes
CONTENT
Content | Write + publish Corporate relocation HR guide | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 5 | Not started
Content | Write + publish SG to Canada guide (2,500 words) | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 6 | Not started
Content | Write + publish SG to USA guide (2,500 words) | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 6 | Not started
Content | Write + publish Moving to Singapore expat guide | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 7 | Not started
Content | Write + publish Pet relocation from Singapore guide | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 8 | Not started
SEO / AEO
SEO / AEO | Media pitches to 3 expat publications | ⚡ Partial | Claude → PR | Marketing | 1.0 hrs | Week 5 | Not started
SEO / AEO | Guest post outreach: 5 Singapore property blogs | ⚡ Partial | Claude + Hunter.io | Marketing | 1.0 hrs | Week 5 | Not started
SEO / AEO | Quora + Facebook expat group answers (5 posts) | ✅ Full automation | Claude → Marketing | Marketing | 0.5 hrs | Week 5 | Not started
SEO / AEO | Build 'Ask APAC' FAQ hub page | ⚡ Partial | Claude → Developer | Developer | 2.0 hrs | Week 6 | Not started
SEO / AEO | Publish 2 guest posts secured from W5 outreach | ⚡ Partial | Marketing | Marketing | 0.5 hrs | Week 6 | Not started
SEO / AEO | AEO test #2: re-run all 10 prompts × 5 engines | ⚡ Partial | Claude + Notion | Marketing | 1.0 hrs | Week 7 | Not started
SEO / AEO | Submit all new content to GSC + Bing | ✅ Full automation | Make + GSC + Bing API | Auto | Auto | Week 7 | Not started
SEO / AEO | Pitch APAC as expert source to 5 publications | ⚡ Partial | Claude → PR | Marketing | 1.0 hrs | Week 8 | Not started
SOCIAL
Social | LinkedIn: 3 posts (HR audience) | ✅ Full automation | Claude + Buffer | Auto | Auto | Week 5 | Not started
Social | Instagram: 3 posts + Reel (piano packing Reel) | ⚡ Partial | Claude + CapCut AI | Social Media | 1.5 hrs | Week 5 | Not started
Social | TikTok: 2 videos (AU customs, SG→London 48hr) | ⚡ Partial | Claude + CapCut AI | Social Media | 1.0 hrs | Week 5 | Not started
Social | YouTube: SG to Australia guide video (5–8 min) | ★ AI-assisted | Claude → Video | Video | 4.0 hrs | Week 6 | Not started
Social | LinkedIn: outreach to 20 HR professionals | ⚡ Partial | Claude + Sales Nav | Marketing | 1.0 hrs | Week 6 | Not started
Social | Instagram: 3 posts + Reel (kitchen packing) | ✅ Full automation | Claude + Canva AI | Auto | Auto | Week 6 | Not started
Social | TikTok: 3 videos from calendar | ✅ Full automation | Claude + CapCut AI | Auto | Auto | Week 6 | Not started
Social | Collect 3 video testimonials from recent clients | ★ AI-assisted | Claude → Customer Svc | Customer Svc | 2.0 hrs | Week 7 | Not started
Social | LinkedIn: corporate Q&A carousel post | ✅ Full automation | Claude + Canva AI | Auto | Auto | Week 7 | Not started
Social | Instagram: testimonial Reel | ★ AI-assisted | Claude → Social Media | Social Media | 1.0 hrs | Week 7 | Not started
Social | TikTok: 2 videos from calendar | ✅ Full automation | Claude + CapCut AI | Auto | Auto | Week 7 | Not started
Social | Google Review target: 20 new reviews | ✅ Full automation | HubSpot automation | Auto | Auto | Week 7 | Not started
Social | LinkedIn: B2B InMail — 50 HR directors | ⚡ Partial | Claude + Sales Nav | Marketing | 1.5 hrs | Week 8 | Not started
Social | YouTube: Corporate relocation HR video | ★ AI-assisted | Claude → Video | Video | 4.0 hrs | Week 8 | Not started
Social | Facebook: paid ad S$500 (SG expat audience) | ★ AI-assisted | Claude → Paid Social | Marketing | 1.5 hrs | Week 8 | Not started
Social | TikTok: 3 videos from calendar | ✅ Full automation | Claude + CapCut AI | Auto | Auto | Week 8 | Not started
REPORTING
Reporting | Phase 2 full report: traffic, AI citations, leads | ⚡ Partial | Claude + GA4 + GSC | Marketing | 1.0 hrs | Week 8 | Not started
MONTH SUMMARY
Total tasks | 30
Fully automated | 9
Partial automation | 16
AI-assisted | 5
Est. total hours | 33 hrs
Est. hours saved by AI | ~15 hrs

## M3 — Acceleration
APAC Relocation ¦ Month 3 — Acceleration
Full video series, maximum AI citation coverage, establish systems for ongoing growth beyond day 90.
✅ Full automation |  | ⚡ Partial (AI drafts, you approve) |  |  | ★ AI-assisted
TASK AREA / DELIVERABLE |  | Automation | AI Tool | Team | Est. Hrs | Week | Status | Notes
CONTENT
Content | Write + publish SG to UAE guide (2,500 words) | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 9 | Not started
Content | Write + publish SG to India guide (2,500 words) | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 9 | Not started
Content | Write + publish Office relocation guide | ⚡ Partial | Claude + Surfer SEO | Marketing | 1.5 hrs | Week 10 | Not started
Content | Write + publish Expat Moving Report 2026 | ⚡ Partial | Claude + Canva AI | Marketing | 2.0 hrs | Week 11 | Not started
Content | Repurpose top 3 blogs → LinkedIn articles | ✅ Full automation | Claude + Buffer | Auto | Auto | Week 11 | Not started
Content | Commission 4 content briefs for Month 4 | ★ AI-assisted | Claude + GSC data | Marketing | 1.0 hrs | Week 12 | Not started
SEO / AEO
SEO / AEO | Submit all new content to Bing Webmaster Tools | ✅ Full automation | Make + Bing API | Auto | Auto | Week 9 | Not started
SEO / AEO | 5 more forum answers — corporate relocation focus | ⚡ Partial | Claude → Marketing | Marketing | 0.5 hrs | Week 9 | Not started
SEO / AEO | Google Business Profile: photos, services, responses | ⚡ Partial | Claude → Marketing | Marketing | 1.0 hrs | Week 10 | Not started
SEO / AEO | Local citations: 4 directories | ★ AI-assisted | Claude → Marketing | Marketing | 1.0 hrs | Week 10 | Not started
SEO / AEO | AEO test #3 — target 3 of 5 engines | ⚡ Partial | Claude + Notion | Marketing | 1.0 hrs | Week 10 | Not started
SEO / AEO | Convert Moving Report into press release | ✅ Full automation | Claude → PR | Marketing | 0.5 hrs | Week 11 | Not started
SEO / AEO | Pitch press release to 5 media outlets | ⚡ Partial | Claude → PR | Marketing | 1.0 hrs | Week 11 | Not started
SEO / AEO | Build 5 backlinks via press release | ✅ Full automation | PR distribution | Marketing | 0.5 hrs | Week 11 | Not started
SEO / AEO | Final AEO test — all 5 engines, all 10 prompts | ⚡ Partial | Claude + Notion | Marketing | 1.0 hrs | Week 12 | Not started
SEO / AEO | Document content production SOP | ✅ Full automation | Claude → Operations | Marketing | 0.5 hrs | Week 12 | Not started
SEO / AEO | Set up monthly AEO monitoring dashboard | ★ AI-assisted | Claude + Looker Studio | Developer | 2.0 hrs | Week 12 | Not started
SEO / AEO | Set up competitor monitoring alerts | ✅ Full automation | Google Alerts + Claude | Auto | Auto | Week 12 | Not started
SOCIAL
Social | YouTube Destination Series Ep 1 + 2 (UK, AU) | ★ AI-assisted | Claude → Video | Video | 6.0 hrs | Week 9 | Not started
Social | LinkedIn: APAC by the numbers infographic | ✅ Full automation | Claude + Canva AI | Auto | Auto | Week 9 | Not started
Social | TikTok: 3 videos (Dubai, UK customs, unusual item) | ✅ Full automation | Claude + CapCut AI | Auto | Auto | Week 9 | Not started
Social | YouTube Destination Series Ep 3 + 4 (AU cities, CA) | ★ AI-assisted | Claude → Video | Video | 6.0 hrs | Week 10 | Not started
Social | LinkedIn InMail: 50 more HR directors | ⚡ Partial | Claude + Sales Nav | Marketing | 1.5 hrs | Week 10 | Not started
Social | TikTok: 2 videos from calendar | ✅ Full automation | Claude + CapCut AI | Auto | Auto | Week 10 | Not started
Social | YouTube Destination Series Ep 5 + 6 (USA, UAE) | ★ AI-assisted | Claude → Video | Video | 6.0 hrs | Week 11 | Not started
Social | Instagram: survey Reel (#1 expat fear) | ✅ Full automation | Claude + Canva AI | Auto | Auto | Week 11 | Not started
Social | TikTok: 3 videos (survey data angles) | ✅ Full automation | Claude + CapCut AI | Auto | Auto | Week 11 | Not started
Social | Facebook: retargeting ad S$500 | ⚡ Partial | Claude → Paid Social | Marketing | 1.0 hrs | Week 11 | Not started
Social | YouTube: India, pet relocation, corporate videos | ★ AI-assisted | Claude → Video | Video | 6.0 hrs | Week 12 | Not started
Social | LinkedIn: 90-day growth update post | ★ AI-assisted | Claude → Marketing | Marketing | 0.5 hrs | Week 12 | Not started
Social | Instagram: Stories series 'Behind the Move' | ⚡ Partial | Claude → Social Media | Social Media | 1.0 hrs | Week 12 | Not started
Social | TikTok: '5,000 moves taught us this' | ✅ Full automation | Claude + CapCut AI | Auto | Auto | Week 12 | Not started
REPORTING
Reporting | Full 90-day audit report | ⚡ Partial | Claude + GA4 + GSC | Marketing | 1.5 hrs | Week 12 | Not started
Reporting | Next-quarter content strategy | ★ AI-assisted | Claude + GSC data | Marketing | 1.0 hrs | Week 12 | Not started
OUTREACH
Outreach | Property agency referral partnership outreach | ★ AI-assisted | Claude → Business Dev | BD | 1.0 hrs | Week 10 | Not started
Outreach | Press release pitches to 5 media outlets | ⚡ Partial | Claude → PR | Marketing | 1.0 hrs | Week 11 | Not started
MONTH SUMMARY
Total tasks | 36
Fully automated | 12
Partial automation | 14
AI-assisted | 10
Est. total hours | 49 hrs
Est. hours saved by AI | ~20 hrs